## query
Created | Estimated Completion Date | Project Debrief Date | Business Unit | Project Number | Project Name | Project Lead | Survey Rate Response | Overall Project Rating | Stage | Category 1 | Key Takeaway 1 | Category 2 | Key Takeaway 2 | Category 3 | Key Takeaway 3 | Suggested Pathforward | Additional Details | Item Type | Path
2026-03-08 20:24 |  | 2026-01-06 | Applicators | 300071 | Applicator Tools Alternative Manufacturer - GreatStar Transition (MOB) | Kyle Jones | 100 | 4.8 | Stage 3 MOB | Opportunity for Improvement | An action item that was discussed is on future projects as packaging is updated to add the prop 65 label to the products. | [6 empty] | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-03-25 15:40 |  | 2026-01-19 | Woodcare | 356482 | Woodcare Alkyd Consolidation | Xiaodong Shi | 85 | 4.5 | 3 | Opportunity for Improvement | Leverage the consolidation practice to other RM categories; RM shifting communication with plants as early as possible; List of preferred and un-preferred RMs to share with technical team | [6 empty] | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-03-25 15:42 |  | 2026-01-12 | Building Materials | 228853 | KST Fabric Free Sprayable Sealant | Michael W Ambrogio | 100 | 4 | 3 | Technical Knowledge/Learning | The strategies utilized to make a sprayable version of One Flash could potentially be used to make other STPE-based products sprayable, if/when there’s a need or desire to do so. | Leverage Finding | The partnership established with Graco could be used for spray testing other products in the future. | Opportunity for Improvement | It would be useful to develop a clearer process to initiate and execute the test batch, labels, and field testing of CBG products. |  |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-04-05 08:55 |  | 2026-03-23 | Applicators | 266760 | Purdy Spirex (Next Generation Brush) | Kirk E Shelhamer | 76 | 3.91 | Gate 3 | Opportunity for Improvement | Earlier Alignment with Brands Marketing/Applicator Marketing/ PSG – The naming, product, and market position of the product worked out, but created lots of timeline compression and stress immediately into Gate 4….ideally we want to achieve these targets coming out of Gate 2 and early in Gate 3. Activities have already started on improving, but needs to be a focus. | Opportunity for Improvement | Innovative Product with Legal Protection – The product is very innovative and cutting edge with all Intellectual Property (IP) completed, but was compressed at the end of Gate 3. Going forward (and already started), we want to start the IP sooner in Gate 2 so that things are not as compressed. | Leverage Findings | Team Collaboration / Hard Work Continues – Multiple examples of excellent Team Collaboration from this Team in overcoming some delays, complexity, and Distribution Concerns (Gate 4). This has been a strength of this Team and need to continue to leverage it! | Actions for Takeaway 1 and 2 have already been started on future Applicator projects and will be an emphasis to check in as projects progress to determine if improvements are seen. |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-04-15 12:05 |  | 2026-04-13 | Paint-NPD | 347860 | Premium Ext Stores UW Base Expansion | Prabhjot K Sahota | 76.9% | 4.8 | SG3 | Technical Knowledge/Learning | Check how manufacturing plants are processing. | Opportunity for Improvement | Spray outs for props - possible to uses quick shots (smaller amount of paint). | Opportunity for Improvement | Is there a way to spread out launches/make and retain product before launching to prevent backup? | If there is a Stage 4 debrief with PTS, ask if there are any manufacturing issues/difficulties like the ones seen in house (C. Novicki). |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-05-11 13:07 |  | 2026-03-04 | Product Technology | 186290 | Forte | Angelo P Mandato | 66% | 3 | 3 | Opportunity for Improvement | Need to improve the procurement process / timing estimates for ordering raw materials to plant for pipeline fill to avoid delays in launch. | Technical Knowledge | Ensure Field Validation is not skipped - feedback from the field is critical to ensuring the project is meeting expectations. Field Validation help us determine to pivot when there was an issue with the prototype. Then the Field Validation on the follow up prototype gave us the confidence to move forward based on the excitement and positive feedback. | Leverage Findings | The Risk Assessment Document that the Engineering team put together was a very helpful tool used to visually communicate with key stakeholders. This should be replicated in future projects where applicable. |  |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-06-05 08:14 |  | 2026-06-01 | Paint-MOB | 285538 and 294299 | HG-706 and WQ1223 to WQ2331 Supply Assurance | Jane C Phillips | 60% | 4.15 | MOB | Leverage Finding/Best Practice | FSET tool and the MOB excel project tracker should be leveraged to future projects. | Opportunity for Improvement | Better alignment with Raw Materials team on polymer recommendation given to control labs since different recommendations were given to architectural and specialty. | Leverage Findings | Frequent update meetings with different teams (internal project team, CE, color, marketing stakeholders, microbiology) were helpful to stay organized and on top of updates for each rex. | Sara Bowers and Sarah Watson to bring feedback to RM team on their polymer recommendation between Brands HG-706 and Building Materials Hg-706 formulas |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-06-18 13:04 |  | 2026-06-16 | Woodcare | 168878 | Helmsman Upgrade | Kevin L Rudd | 42% | 4.5 | 3 | Leverage Finding/Best Practice | Partnering with other teams such as Marketing, CE, PTS, Medina, P&M, Microbiology Lab & plants was key in execution & meeting timeline. | Opportunity for Improvement | Labman images need improvement. Visits to Medina were helpful, but needed to help prepare for gate review. | Leverage Findings | Getting new products on Pipeline early was very helpful for the plants & PTS | Open a CIP to improve Labman images |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-06-22 10:17 |  | 2026-04-24 | Paint-NPD | 236479 | Symmetry Phase 1 | Randy R Chamberlain | 57% | 4 | 3 | Leverage Finding/Best Practice | Bi-weekly project update meetings between Marketing and Technical. Good cadence to update Marketing and keep technical team aligned. | Leverage Finding | The use of a project tracker during bi-weekly update meetings was helpful to understand status of key deliverables. | Leverage Findings | The use of Order of Addition Engineering templates in early stage 2 development to ensure processing parameters are optimized prior to formula installation scale ups. | Discuss leveraging during recurring PT / Comm CI roundtable . Discuss leveraging during recurring PT / Comm CI roundtable. Discuss leveraging during recurring PT / Comm CI roundtable |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-06-22 10:22 |  | 2026-04-21 | Paint-NPD | 269261 | Low VOC Primer | Thomas A Dereska | 48% | 4.5 | 3 | Leverage Finding/Best Practice | Piloting earlier in Stage 2 to ensure that the customer would be good with the performance and the prototype was feasible before beginning Stage 3. | Leverage Finding | Sending PLS’ earlier could help speed up awareness of site but making sure that RTS for labels is close so plant doesn’t get frustrated being told that they need to make without being able to order labels. | Technical Knowledge | The EPS resin WQ1349P showed very good performance and is currently being evaluated in other interior / exterior architectural areas. | Discuss during recurring PT / Comm CI roundtable, potential update to project timeline |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-07-14 14:43 |  | 2026-07-08 | Woodcare | NAV 245974 / 65607 | Krylon Harmony & Minwax One Step | Alexzondria Harris | 71% | 3.67 | 4 | Leverage Finding/Best Practice | Add projects to pipeline on gate 2 once there is customer commitment. This would alleviate last minute constraints on the sites. | Opportunity for Improvement | Update audit plan and process with timeline for audits requiring both aerosol and concentrates. Having the PLS issues earlier for launches where both is needed would be helpful as well. | Technical Knowledge | Getting document sent out to various teams for different PLS launch terms. Having the alignment on launch definitions will help all teams with planning and ensuring we're meeting customer required date early on. Drive alignment for what is communicated on pipeline vs commercialization meetings vs PLS updates. |  |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-08-06 12:23 |  | 2026-08-05 | Paint-NPD | 287632 & 368579 | Latitude Low Lustre NPD & Satin MOB Grit/Syneresis Mitigation | Jessica A Mewhinney | 73 | 4.09 | 3 | Technical Knowledge/Learning | Understanding that the presence of phosphorous in grit when TKPP is present is not necessarily indicative of traditional phosphate seeding. The imbalance of phosphate containing anionic surfactants and other ionic species in the formula can contribute to grit formation. | Leverage Finding | Using frequency sweep and LUMiSizer tools in combination for early assessment of prototypes for mitigating syneresis in heat stability testing. | Opportunity for Improvement | Assessing the risk of a quick timeline to launch at the beginning of the project from a technical and product planning aspect. Understanding the risk to quality and timing when stability cannot be fully assessed within development and when there are competing priorities of products going through pipeline and quality audit at the same time. |  |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-08-10 13:08 | 2026-07-30 | 2026-07-30 | Aerosol | 201952 | Propellant Consolidation - Aerosol Excellence | Alex Hankins | 43% | 3.67 | 3 | Technical Knowledge/Learning | VOC/MIR changes on several formulas pushed them out of regulation and put them on hold. | Opportunity for Improvement | Ensure cadence of project updates is agreed upon by all team members. A risk flowchart detailing effects of project changes (testing requirements, durations, etc.) on key deliverables would help facilitate better discussions between technical and management. This would help with laying out what is mandatory vs ideal. | Opportunity for Improvement | For larger initiatives/projects, breakout project tasks/requirements into smallest reasonable segments possible. The aerosol team’s “Rust Bulk” project is a good approach/template for work delegation. One item to note is that the “Rust Bulk” project did have more resources available. | Ensure alignment with regulatory team throughout life of project for any projects with formula raw material mass changes. Regulatory can pull/check VOCs/MIRs before pushing the mass change to check if any need adjusted. |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings
2026-08-12 13:49 |  | 2026-08-06 | Quality | NAV 336496 | DPM: Duraclean Interior UW | Alexzondria Harris | 72 | 2.5 | 4 | Opportunity for Improvement | SDS review for concerning language prioritizing solvents/cosolvents to spot differences between vendors. | Opportunity for Improvement | List of site specific restrictions to share with the broader team --which sites have which restrictions (respirable dust, static dissipating, combustibles etc...) | Opportunity for Improvement | Make MOC timeline and overall process visible to all stakeholders |  |  | Item | sites/StageGateDebriefteam/Lists/Debrief Findings