## query
Created | Estimated Completion Date | Project Debrief Date | Business Unit | Project Number | Project Name | Project Lead | Survey Rate Response | Overall Project Rating | Stage | Category 1 | Key Takeaway 1 | Category 2 | Key Takeaway 2 | Category 3 | Key Takeaway 3 | Suggested Pathforward | Additional Details | Item Type | Path
2026-01-08 09:12 | 2026-01-20 | 2026-01-15 | Aerosols | 900101 | Valve Reliability Improvement | Jordan Lee | 72% | 4.1 | Stage 3 | Technical Knowledge/Learning | Early supplier testing reduced late design changes and gave the team better confidence before pilot scale. | Opportunity for Improvement | Define packaging constraints earlier so formula and operations teams can resolve tradeoffs before gate review. | Leverage Finding/Best Practice | Weekly risk reviews helped the team keep decisions visible and should be reused for similar projects. | Use the risk review template during the next aerosol project kickoff. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-01-18 14:25 | 2026-01-28 | 2026-01-27 | Applicators | 900102 | Brush Handle Material Trial | Taylor Morgan | 81% | 4.45 | Stage 3 | Leverage Finding/Best Practice | Prototype reviews with manufacturing helped identify tooling concerns before the final design freeze. | Technical Knowledge/Learning | A short durability screen can predict field issues well enough to prioritize the best concepts. | Opportunity for Improvement | Marketing claim language should be reviewed earlier when a material substitution is planned. | Add claim review to the gate checklist. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-02-03 10:05 | 2026-02-20 | 2026-02-18 | Building Materials | 900103 | Sealant Cure Time Optimization | Avery Chen | 64% | 3.9 | Stage 4 | Opportunity for Improvement | Testing windows were compressed because raw material alternates were not approved early enough. | Technical Knowledge/Learning | Humidity sensitivity should be included in future qualification plans for similar sealant changes. | Leverage Finding/Best Practice | The shared test tracker improved visibility across lab, plant, and commercial partners. | Keep the tracker active through launch readiness. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-02-14 16:30 | 2026-03-01 | 2026-03-06 | Paint-MOB | 900104 | Resin Supply Assurance Update | Morgan Patel | 58% | 3.55 | MOB | Opportunity for Improvement | Backup raw material timing needs clearer ownership when supply risk emerges mid-project. | Leverage Finding/Best Practice | Regular procurement touchpoints helped maintain launch confidence during supplier transitions. | Technical Knowledge/Learning | A decision tree for resin alternates would reduce cycle time on future supply projects. | Create an escalation path for supplier risk decisions. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-03-02 08:40 | 2026-03-10 | 2026-03-08 | Paint-NPD | 900105 | Interior Finish Refresh | Casey Rivera | 77% | 4.6 | SG3 | Leverage Finding/Best Practice | Early customer feedback helped the team narrow options before expensive scale-up work began. | Technical Knowledge/Learning | Small batch color checks gave reliable enough direction for the first commercial decision point. | Opportunity for Improvement | Launch timing assumptions should include more buffer for label approvals. | Reuse the customer feedback approach for the next finish refresh. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-03-20 11:18 | 2026-04-05 | 2026-04-01 | Product Technology | 900106 | Accelerated Weathering Method | Riley Brooks | 69% | 4.25 | Stage 3 | Technical Knowledge/Learning | The accelerated test method aligned well with outdoor exposure results for the first two validation panels. | Leverage Finding/Best Practice | Cross-functional review of test data improved confidence in method adoption. | Opportunity for Improvement | Document sample preparation steps more tightly to reduce variation between labs. | Publish the method checklist before the next validation run. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-04-04 13:45 | 2026-04-12 | 2026-04-18 | Quality | 900107 | Complaint Coding Standardization | Jamie Scott | 91% | 4.05 | Stage 4 | Opportunity for Improvement | Teams used inconsistent reason codes, which made trend analysis slower than expected. | Leverage Finding/Best Practice | A short training session improved adoption more than written guidance alone. | Technical Knowledge/Learning | Dashboards need clear examples next to each code to support consistent entry. | Add example definitions to the coding guide. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-04-22 09:55 | 2026-05-08 | 2026-05-02 | Woodcare | 900108 | Deck Stain Tint Expansion | Drew Bennett | 66% | 3.8 | Stage 3 | Technical Knowledge/Learning | Tint strength varied more by base than expected and should be checked earlier in future expansions. | Opportunity for Improvement | Retail sample timing was not visible enough to technical leads during the final review window. | Leverage Finding/Best Practice | The color approval summary helped leadership make faster scope decisions. | Add retail sample milestones to the project plan. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-05-07 15:10 | 2026-05-25 | 2026-05-22 | Applicators | 900109 | Roller Cover Line Simplification | Parker Kim | 74% | 4.35 | Stage 3 | Leverage Finding/Best Practice | A focused SKU rationalization workshop quickly separated must-have products from low-value complexity. | Opportunity for Improvement | Distribution impacts should be validated before final assortment decisions are locked. | Technical Knowledge/Learning | Plant trial data was most useful when grouped by fiber family rather than SKU. | Schedule distribution validation before gate approval. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-05-24 12:00 | 2026-06-05 | 2026-06-10 | Paint-NPD | 900110 | Exterior Primer Performance Boost | Quinn Walker | 62% | 4.75 | SG4 | Technical Knowledge/Learning | Adhesion improvements were strongest on aged substrates, which should shape the future claims plan. | Leverage Finding/Best Practice | Combining field and lab panels gave the team a stronger evidence package for launch readiness. | Opportunity for Improvement | The field panel calendar needs earlier confirmation to avoid late-season testing pressure. | Build the claims evidence package earlier in Stage 3. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-06-12 10:42 | 2026-06-25 | 2026-06-20 | Woodcare | 900111 | Fence Coating VOC Reduction | Sam Ellis | 55% | 3.4 | Stage 4 | Opportunity for Improvement | VOC reduction work created unexpected dry-time tradeoffs that were not visible in the initial plan. | Technical Knowledge/Learning | Application thickness had a larger impact on perceived dry time than formula variation. | Leverage Finding/Best Practice | Plant operators provided practical adjustments that improved first-pass manufacturability. | Include dry-time tradeoff review in future low-VOC projects. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-07-03 14:05 | 2026-07-16 | 2026-07-14 | Aerosols | 900112 | Spray Pattern Consistency Study | Alex Harper | 88% | 4.2 | Stage 3 | Leverage Finding/Best Practice | Video review of spray patterns helped align subjective evaluations across the project team. | Technical Knowledge/Learning | Nozzle age and fill temperature were the biggest drivers of pattern variation. | Opportunity for Improvement | The team needs a clearer approval threshold for borderline spray pattern results. | Define spray pattern acceptance limits before the next study. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-07-21 09:30 | 2026-08-01 | 2026-08-07 | Paint-MOB | 900113 | Plant Transfer Readiness | Emerson Gray | 47% | 3.25 | MOB | Opportunity for Improvement | Training materials arrived too late for operators to practice the revised process before transfer. | Technical Knowledge/Learning | The readiness checklist needs to separate documentation completion from operator confidence. | Leverage Finding/Best Practice | Daily transfer huddles helped resolve open items quickly once the team was onsite. | Start operator training earlier for future transfers. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs
2026-08-09 08:15 | 2026-08-22 | 2026-08-19 | Quality | 900114 | Batch Release Review Pilot | Jordan Avery | 79% | 4 | Stage 4 | Technical Knowledge/Learning | The review pilot showed that most release delays came from missing context rather than missing data. | Opportunity for Improvement | Exception criteria should be clearer so reviewers know when escalation is required. | Leverage Finding/Best Practice | A short pre-review checklist reduced rework and improved meeting quality. | Refine exception criteria and expand the checklist pilot. | Synthetic sample record for dashboard testing. | Item | synthetic/project-debriefs